# Title: CPQ Weekly Status Report -13 Jan 2020

|  |  |  |
| --- | --- | --- |
| **Status Updated Date** | **Owners** | **Escalation Matrix** |
| FreshSales | PM - [Swati Sharma](https://confluence.freshworks.com/display/~swati.sharma)  Arch - [Sivalingam Selvasekaran](https://confluence.freshworks.com/display/~sivalingam.selvasekaran)  EM - [Jayaprakash Ramakrishnan](https://confluence.freshworks.com/display/~jayaprakash.ramakrishnan)  TPM - [Preethi Mahalingam](https://confluence.freshworks.com/display/~preethi.mahalingam) | [Mariappan Vaithilingam](https://confluence.freshworks.com/display/~mariappan.vaithilingam) |

### Program Summary

CPQ (Configure, Price, Quote) will be an add on product in Freshsales to enable Freshsales customers to create products and quotations. Entire development program has been divided into two parts. On a high level those are given below.

1. CPQ V1 which includes the ability to  create products in Freshsales and add them to the deals . Epic link - <https://freshworks.freshrelease.com/FSALES/issues/FSALES-14008>
2. CPQ V2 which includes the ability to create quotations and offer it to customers. Epic link - <https://freshworks.freshrelease.com/FSALES/issues/FSALES-15661>

### Milestones and Current Status

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # | Milestone | Sprint demo  Date | Last Week  (06-Jan-2020) | This Week  ( 13-Jan-2020) | Comments |
| M1 | End to end working product with product creation capability. | 28 Jan 2020 | IN PROGRESS | IN PROGRESS | Two squads, Petta and Sleeper cells, are working on this. Only create product functionality will be in the demo.  Initial milestone date was Jan 21st. However as Sleeper cells couldn't start working on it due to other priorities, date has been revised. |
| M2 | Completion of CPQ V1 stories. | 10 Mar 2020 | IN PROGRESS | IN PROGRESS | This is a major milestone to track the delivery of entire CPQ V1 stories. |

### **Action Items**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| [S.no](http://S.no) | Action Item | Owner | ETA | Current Status |
| 1 | Review V2 user stories | Jayaprakash | 28 Jan 2020 | IN PROGRESS |
| 2 | Create subtasks for V2 | Jayaprakash | 28 Jan 2020 | Yet to be started. |
| 3 | Estimate V2 stories | Jayaprakash | 28 Jan 2020 | Yet to be started. |

### Dependencies

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| # | Dependencies | Team | FreshRelease Ticket | ETA | Status | Comments |
| 1 | API review by standardisation team. | API standardisation team | [FSALES-15215](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15215) | 03 Mar 2020 | Open | Swagger project will be created and shared with the team for review. |

### Risks & Mitigation

|  |  |  |  |
| --- | --- | --- | --- |
| # | Risk | State | Mitigation |
| 1 | V2 stories are yet to be signed off and estimated. A bigger scope may skip the GA which is planned for end of Q1. | Open | V2 stories will be estimated by Jan 28. Resource allocation will be planned after that. |
| 2 |  |  |  |

### Work Breakdown Status

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S.No | FreshRelease | Description | Squad | ETA | Last Week  (06-Jan-2020) | This Week  ( 13-Jan-2020) | Comments |
| 1 | [FSALES-15177](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15177) | UI- Product segments CRUD | Petta | 21 Jan 2020 | IN PROGRESS | IN PROGRESS | On track |
| 2 | [FSALES-15183](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15183) | UI - Filters page - Column customization | Petta | 21 Jan 2020 | IN PROGRESS | IN PROGRESS | On track |
| 3 | FSALES-16044 | Form service integration | Petta | 21 Jan 2020 | IN PROGRESS | IN PROGRESS | On track |
| 4 | [FSALES-15213](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15213) | Product schema | Sleeper cells | 20 Jan 2020 | Not started | Not started | Task may spill over due to other priority items in the squad. |
| 5 | [FSALES-15215](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15215) | Product, Product Custom Fields CRUD APIs | Sleeper cells | 20 Jan 2020 | Not started | Not started | Task may spill over due to other priority items in the squad. |
| 6 | [FSALES-16302](https://freshworks.freshrelease.com/FSALES/issues/FSALES-16302) | Product API at micro service | Sleeper cells | 20 Jan 2020 | Not started | Not started | Task may spill over due to other priority items in the squad. |
| 7 | [FSALES-15565](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15565) | Customer module generalization | Petta | 10 Dec 2019 | CLOSED |  |  |
| 8 | [FSALES-15171](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15171) | Filters page Skeleton setup | Petta | 10 Dec 2019 | CLOSED |  |  |
| 9 | [FSALES-15175](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15175) | Product List page set up | Petta | 24 Dec 2019 | CLOSED |  |  |
| 10 | [FSALES-15176](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15176) | Filters search facet | Petta | 24 Dec 2019 | CLOSED |  |  |
| 11 | [FSALES-15173](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15173) | UI - Add/Edit Product Modal | Petta | 07 Jan 2020 | CLOSED |  |  |