# Title: CPQ Weekly Status Report -20 Jan 2020

|  |  |  |
| --- | --- | --- |
| **Status Updated Date** | **Owners** | **Escalation Matrix** |
| FreshSales | PM - [Swati Sharma](https://confluence.freshworks.com/display/~swati.sharma)  Arch - [Sivalingam Selvasekaran](https://confluence.freshworks.com/display/~sivalingam.selvasekaran)  EM - [Jayaprakash Ramakrishnan](https://confluence.freshworks.com/display/~jayaprakash.ramakrishnan)  TPM - [Preethi Mahalingam](https://confluence.freshworks.com/display/~preethi.mahalingam) | [Mariappan Vaithilingam](https://confluence.freshworks.com/display/~mariappan.vaithilingam) |

### Program Summary

CPQ (Configure, Price, Quote) will be an add on product in Freshsales to enable Freshsales customers to create products and quotations. Entire development program has been divided into two parts. On a high level those are given below.

1. CPQ V1 which includes the ability to  create products in Freshsales . Epic link - <https://freshworks.freshrelease.com/FSALES/issues/FSALES-14008>
2. CPQ V2 which includes the ability to create quotations and offer it to customers. Epic link - <https://freshworks.freshrelease.com/FSALES/issues/FSALES-15661>

### Milestones and Current Status

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # | Milestone | Sprint demo  Date | Last Week  (13-Jan-2020) | This Week  ( 20-Jan-2020) | Comments |
| M1 | End to end working product with product creation capability. | 28 Jan 2020 | IN PROGRESS | IN PROGRESS | A demo is planned for January 28, 2020. Two squads, Petta and Sleeper cells, are working on this. Only create product functionality will be in the demo. |
| M2 | Product list view, search, bulk actions. | 11 Feb 2020 | Not started | IN PROGRESS | Both Petta and Sleeper cells squads are working on this. A demo is planned for 11 Feb 2020 on product list view, search and bulk actions. |
| M3 | Completion of CPQ V1 stories. | 10 Mar 2020 | IN PROGRESS | IN PROGRESS | This is a major milestone to track the delivery of entire CPQ V1 stories. |

### **Action Items**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| [S.no](http://S.no) | Action Item | Owner | ETA | Current Status | Comments |
| 1 | Review V2 user stories | Jayaprakash | 28 Jan 2020 | IN PROGRESS | 28 Jan 2020 In this task, We are planning to go through all CPQ V2 user stories to ensure all open questions get clarified by PM. ETA may skip as developers are fully equipped with V1 stories. One week  delay is expected. |
| 2 | Create subtasks for V2 | Jayaprakash | 28 Jan 2020 | IN PROGRESS | 28 Jan 2020 ETA may skip as developers are fully equipped with V1 stories. One week delay is expected. |
| 3 | Estimate V2 stories | Jayaprakash | 28 Jan 2020 | IN PROGRESS | 28 Jan 2020 ETA may skip as developers are fully equipped with V1 stories. One week delay is expected. |

### Dependencies

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| # | Dependencies | Team | FreshRelease Ticket | ETA | Status | Comments |
| 1 | API review by standardisation team. | API standardisation team | [FSALES-15215](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15215) | 03 Mar 2020 | Open | Swagger project will be created and shared with the team for review. |

### Risks & Mitigation

|  |  |  |  |
| --- | --- | --- | --- |
| # | Risk | State | Mitigation |
| 1 | V2 stories are yet to be signed off and estimated. A bigger scope may skip the GA which is planned for end of Q1. | Open | Resource allocation will be planned after V2 stories estimation. Based on the current status it will happen only in the February first week. |
| 2 |  |  |  |

### Work Breakdown Status

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S.No | FreshRelease | Description | Squad | ETA | Last Week  (13-Jan-2020) | This Week  ( 20-Jan-2020) | Comments |
| 1 | [FSALES-15177](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15177) | UI- Product segments CRUD | Petta | 21 Jan 2020 | IN PROGRESS | IN PROGRESS | On track |
| 2 | [FSALES-15183](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15183) | UI - Filters page - Column customisation | Petta | 21 Jan 2020 | IN PROGRESS | IN PROGRESS | On track |
| 4 | [FSALES-15213](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15213) | Product schema | Sleeper cells | 28 Jan 2020 | IN PROGRESS | IN PROGRESS | Task is expected to be completed for the demo on 28 Jan 2020 |
| 5 | [FSALES-15215](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15215) | Product, Product Custom Fields CRUD APIs | Sleeper cells | 28 Jan 2020 | Not started | IN PROGRESS | Task is expected to be completed for the demo on 28 Jan 2020 |
| 6 | [FSALES-16302](https://freshworks.freshrelease.com/FSALES/issues/FSALES-16302) | Product API at micro service | Sleeper cells | 28 Jan 2020 | Not started | IN PROGRESS | Task is expected to be completed for the demo on 28 Jan 2020 |
| 7 | [FSALES-15224](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15224) | Implement Filter and Search | Sleeper cells | 03 Feb 2020 | Not started | Not started | Task planned to be completed by end of current sprint of Sleeper cells. |
| 8 | [FSALES-15217](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15217) | Support for bulk actions | Sleeper cells | 03 Feb 2020 | Not started | Not started | Task planned to be completed by end of current sprint of Sleeper cells. |
| 9 | FSALES-16151 | WILL filter integration | Petta | 04 Feb 2020 | Not started | Not started | Task planned to be completed by end of next sprint of Petta. |
| 10 | [FSALES-15565](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15565) | Customer module generalisation | Petta | 10 Dec 2019 | CLOSED |  |  |
| 11 | [FSALES-15171](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15171) | Filters page Skeleton setup | Petta | 10 Dec 2019 | CLOSED |  |  |
| 12 | [FSALES-15175](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15175) | Product List page set up | Petta | 24 Dec 2019 | CLOSED |  |  |
| 13 | [FSALES-15176](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15176) | Filters search facet | Petta | 24 Dec 2019 | CLOSED |  |  |
| 14 | FSALES-16044 | Form service integration | Petta | 21 Jan 2020 | IN PROGRESS | CLOSED |  |
| 15 | [FSALES-15173](https://freshworks.freshrelease.com/FSALES/issues/FSALES-15173) | UI - Add/Edit Product Modal | Petta | 07 Jan 2020 | CLOSED |  |  |